## Sheet1
Risk | Description | Assumptions | Probability |  |  |  |  | Consequences |  |  |  |  | Probability/Consequences | Treatment |  | Risk
Risk |  |  | VL | L | M | H | VH | VL | L | M | H | VH | Justification | Type | Measure(s) | Owner
Risk | Interface Integration setbacks | ISHR system is a blackbox with little information about it | [10 empty] | Because of the blackbox nature of the ISHR system, it is likely that unexpected problems will be found while integrating our interface, which can lead to a delay of the work package | Mitigation | Ask for documentation or more information regarding the ISHR system | Tech Tics | bar: Probability M; Consequences L
Risk | HRD Emplloyees not cooperating due to unhapiness | HRD employees were unmotivated due to the recent news of change | [10 empty] | The making of this new system can lead to some workers to be cut from the client company. This can raise the unhapiness of the HRD employees leading to some uncooperation from their part, delaying our work which involves their cooperation | Deflection | Let the client negotiate with its employees | Client | bar: Probability L; Consequences H
Risk | HRD Delegate leaving the project | HRD Delegate has recieved na offer from another company | [10 empty] | The HRD Delegate is a very important piece of our project, as he will be not only be our main consultant from the client side as he will also decide on the Corporate Information Module functionalities. If his departure happens on the early stages of the project, it will majorly delay our schedule | Deflection | Let the client negotiate with the HRD Delegate; Have another person ready to take over in case of his departure. | Client | bar: Probability M; Consequences H
Risk | Bad quality of data to be migrated | Experience tells us this kinds of files do not have a global standart applied to them | [10 empty] | Our team will need to create scripts in order to migrate the existing Excell files from the old system to our new system. If these files do not have a standart we would need to create multiple scripts or change them by hand, greatly increasing the work load. | Mitigation | Add an allowance of 2 days in case the data is not on a standart and we need to change or create extra scripts | Client | bar: Probability H; Consequences L
Risk | Technical Coordenator leaving the project | Technical Coordenator has been working in the company for a long time and is looking for different challenges | [10 empty] | Our Technical Coordenator is involved in 82% of all work packages and executes 64% of these. His departure would cause disastrous effects on our project with inumerous delays on the workflow. | Contingency | Have another person monitoring the project and be ready to takeover in case of his departure. | Tech Tics | bar: Probability M; Consequences VH
6 | Machines not arriving on time and/or in conditions | Hardware may not be available on the expected time | [10 empty] | If the arrival date or good state of the machines is not assured it can cause some delays on the project | Mitigation | Remind and warn the client to obtain and check the machines in advance | Tech Tics | bar: Probability L; Consequences L